## Sheet1
Story ID | Story Name | Description | Priority | Iteration (Sprint) number | Acceptance Criteria | Notes | Date started (actual date) | Date finished (actual date)
US01 | User sign up | As a user I want I can sign up the system with my email together with some optional body characteristic. So that coach or the system can better custom some classes for me. | very high | 1 | Make sure the telephone number/ email is not used by other people Receive the user’s phone/email, name,password, gender(o), weight(o), height(o), age(o) Generate user entity with above information, store in the memory.
UL01 | User log in | As a user I want I can sign in just with my phone/email and password So that i can save more time | very high | 1 | Use email/phone as ID of the user Use password to make sure if the user have the authority to login If password wrong, show the message If user entity not exist, show the message.
A01a | Watch video | As a customer I want to watch some fitness videos So that I can correct my movements, avoid sports hurt and achieve better fitness effect | very high | 1 | Make sure the video plays properly Make sure the video is useful
A06a | Wallet | As a user, I want to be able to save money to the wallet in this application, so that I don't need to make payments after switching to other paying applications. | very high | 1 | Wallet should be in the personal information interface.
B01g | Live session | As a user I want my personal coaches can have live sessions for me So that I can exercise with my coach together to gain my motivation | very high | 1 | Make sure that there will be live sessions for the personal lessons
US02 | User sign up legality | As a staff of the gym I want the user sign up procedure can make sure the phone/email is legal and password is encrypted So that the system can be more safe | high | 1 | Make sure the phone/email is legal Make sure the stored password is encrypted once stored in memory | implementation of US01
MS05 | Reliable data storage | As a staff I want a reliable data storage system during our developing process. So that it will be safer to store the user’s data. | high | 1 | Design and implement a well design data storage interface
B01a | show personal coach information | As an employee I want to obtain a coach’s name, address, phone number,date of birth, sex, age, height, weight, fitness projects to form the coach’s information So that I get the coach's information and know better about the coaches | high | 1 | Verify that the coach does not exist in system Make sure the information about the coaches is correct
B01b | Choose a personal coach | As a user I want to choose my own coach according to their information and my own situation. So that I can find the fitness coach for me | high | 1 | Make sure the important information about the coaches are shown to the users Make sure the information is timeliness and correct
B01c | Book the lessons | As a user I want to book a coach’s class in advance So that I can manage my time better and I don’t have to worry about not finding a coach. | high | 1 | Make sure one coach won’t attend classes for more than one customers at the same time, unless the customer has special needs Make sure the user can choose the time which is not booked for another user Make sure the coach the user has booked is the one the user has designated Make sure the user can’t book a coach half an hour before class starts
US01G | User sign up GUI | As a staff of gym I want the sign up surface is clean and easy to use, where have some notice to introduce user to sign up So that it will not let people who want to register to give up because of the complicated interface | medium | 1 | Make sure there is sign up link in sign in interface Make sure there is only email/phone, password, name , weight height shown Make sure the sign up procedure is done with continuously interface for good design
UL01G | user login GUI | As a staff I want the GUI of login can be shown once user open the system and after the login procedure, it will jump to the home page So that i can have better user experiment | medium | 1 | Once the system start, the login page will show out After the login procedure finish, it will change to the home page
MS01 | Set up different membership | As a user I want to get higher membership when I recharge more money and get So that I can enjoy some specific service | medium | 2 | According to the money that they recharged, they can set to different membership Once a recharge procedure finish, check if the total recharged money is enough to upgrade membership For different membership, set up some rights for them to use
B01d | Check the booked time | As a user I want to check the booked time for a certain coach So that I can know which time the coach is free and I can book | medium | 2 | Make sure the time for every coaches is correct Make sure the eating and resting time for a coach cannot be booked Make sure the user can check the booked and free time clearly Make sure that the coach need a 30 minutes break after every lessons
B02a | Check booked coaches | As a user I want to see the details about the lessons I have booked but haven’t taken yet So that I can have a better knowledge about my lessons | medium |  | Verify the details include the coach’s name, the class date and the class time Make sure all the classes which is booked but not taken yet can be seen by the user clearly
B03a | Cancel the classes | As a user I want to be confirmed before cancel the classes So that I will not cancel the class which I don’t want because of a false touch | medium | 2 | Make sure the time taken by the course that has been withdrawn becomes idle Make sure the customer can’t cancel the course within six hours before class Make sure that there will be a pop-up window to confirm whether to withdraw before the user withdraws
A01b | Video can be classified | As a customer I want the video can be classified, such as hit training, warm-up training, etc So that I can quickly find the video I want to watch | medium | 3 | Make sure the classification accurately Make sure the user can find the right video easily
B05a | Goal setting module | As a user I want to set workout goals So that I can get motivated to exercise | medium | 3 | ·Make sure there are enough kinds of target, for example, weight-reducing, muscle-building and total time of exercise, etc. ·Verify that there is free to set quantity of target. ·Verify that there is a text box for additional remarks.
B07a | Trainer Evaluation | As a prudent user I want to see the evaluation of every trainer So that I can check whether the trainer is responsable and the guidance is effective to avoid wasting money. | medium | 3 | ·Verify the evaluation module contains all reviews, favorable reviews, medium reviews and bad reviews. ·Verify the number of favorable reviews, medium reviews and bad reviews are shown.
B07b | Write trainer evaluation | As a user I want to write evaluation of my trainer. So that I can recommend him/her to other users or write my complaint about the trainer to protect my right. | medium | 3 | ·Verify only the users trained by the trainer can write reviews. ·Verify that user can comment under others’ reviews. ·Verify that pictures can be uploaded to reviews. ·Verify the complaint part reminds users to choose complaints type and write the detail.
B07c | Report problems to customer service | As a user I want to see the convienient way to report problems to customer service So that I can communicate directly with the company to resolve disputes | medium | 3 | ·Verify customer hotline is put on conspicuous position ·Verify there are many ways to communicate except making telephone calls (email, Wechat public account etc)
A02a | Browsing History | As a user, I want to watch videos with browsing history, so that I can continue watching the video from where I left off. | medium | 3 | When we click on the video, we can choose to continue watching or start from the beginning.
A03a | Favorites | As a user, I want to be able to save favorites on London Fitness application, so that I can choose from a finite drop-sown list to easily locate the videos I like. | medium | 3 | We can rename your favorites. We can create multiple favorites by ourselves.
A05a | Comment | As a user, I want to comment below videos, so that I can make comments and watch videos separately. | medium | 3 | When videos are played in full screen, comments are displayed below.
A05c | Report | As an administrator, I want to report bad videos, so that I can remove those videos and punish the author. | medium | 3 | Be reported once seal 1 week, be reported twice permanent seal.
MS02 | Set up bargain for recharge money | As a staff I want the more money they recharge, the more bargain they can get So that user will be likely to deposit more money to the system | low | 2 | Set different bargain for different deposit level Receive the user id, return current money and update membership
MS03 | Set up 7 day free for video | As a staff I want the new user can try to use the system without limitation for 7 days So that they can adapt to the system and can increase user retention | low | 4 | Set create time for user entity to compute the day to decide whether he can user the privilege Check the authority when the user update
MS04 | Invitation code | As a user I want that new users can register with old user’s invitation code. So that both the new and old users are able to earn some discount. | low | 4 | Generate and store the user’s invitation code and compare them when needed. Design the discount strategy.
MS05 | Family membership | As a user I want that users can register and purchase membership card in family unit. So that the whole family can share the membership and get some discount | low | 4 | Set different membership type and design different membership discount strategy
B01e | place of coach’s schedule | As a user I want the coach's schedule can be at the top of the coach's information So that I can see the time schedule for the coach clearly and I can book lessons easily | low | 3 | Make sure the schedule of the coach is clear and easy to distinguish
B01f | place of “book” option | As a user I want the “book” option next to the coach's schedule So that I can book lessons I want easily according to the time schedule | low | 3 | 1.Make sure the “book” button is clear to the user 2.Make sure the user can choose the time to book a lesson after click the “book” button
B02b | Check the past lessons | As a user I want to check the details for the lessons that I have taken So that I can check if there is something wrong and I can know the name and information about the past coaches. | low | 2 | Verify the details include the coach’s name, the class date, the class time and the price Make sure all the classes which is booked and have taken yet can be seen by the user clearly
B02c | GUI of the booked lessons | As a user I want to an see the scheduled course time of the booked coaches which is sorted descending by time So that I can see the booked course time easily and check the time clearly | low | 3 | 1.Make sure the time for every lesson is clear for the user 2.Make sure the time is followed by the coach’s name and date
B02d | place of the booked lessons | As a user I want the “past lessons” button next to the “booked lessons” on the top So that I can change to view the past lessons clearly | low | 3 | 1.Make sure the “past lessons” button is as big as the button of “booked lessons” 2.Make sure the “past lessons” button is clear for the users
B03b | place of the “cancel” option | As a user I want the button of “cancel” can be found when I check the booked lessons So that I can cancel the lessons I booked easily according to the time | low | 3 | 1.Make sure the “cancel” button appears on the scheduled course page 2.Make sure that for every booked but have not taken lessons, there is a cancel “button” at the end of the information of this lesson
A01c | Individualized video recommend | As a customer I want to be recommended fitness videos based on my personal situation So that I can make a fitness plan that suits me best and achieve better fitness effect | low | 4 | Make sure to select the right videos based on the user profile(height, weight, etc)
A01d | Random video recommendation | As a customer I want to have a random course recommendation So that I can find some interesting new ways to get fit | low | 5 | Make sure the recommendation courses are different every time you open the app
B05b | Degree of goal completion | As a user I want to see degree of goal completion after every workout So that I can see my progress during the long period of workout | low | 4 | ·Verify there is a plot in the goal module to show the degree of goal completion ·Verify the plot shows the dates of every workout.
B05c | Goal modification | As a user I want to modify workout goal So that I can adjust my goal after considering the real training situation to make it higher or lower. | low | 4 | ·Verify that there is a modification button after user set goals.
A04a | Watch Later | As a user, I want to be able to conveniently add the unfinished videos into a folder called 'watch later', so that I will remember to watch those I have not finished watching but still want to watch later. | low | 4 | Next to the Favorites.
A05b | Likes | As a user, I want to give likes to videos, so that I can watch videos with many likes. | low | 4 | The same kind of video, the first recommendation of high praise.
MS06 | Family membership for kids | As a user I want that kids can have discount or be free of charge in family membership. So that it will be more attractive to the family with kids. | very low | 5 | Set different membership type and design different membership discount strategy.
B04a | Recommended coach algorithm | As a employee I want to have an algorithm to select the most suitable coach according to the user's information So that the recommended coach can be easily found for every user | very low | 5 | Make sure the algorithm is rigorous, is a comprehensive user of all kinds of information Make sure every user can have at least two recommended coaches
B04b | place of recommended coaches | As a user I want the recommended coaches can be seen at the top of the select coach interface So that I can find the recommended coaches easily | very low | 5 | 1.Make sure the recommended coaches are clear and easy to find 2.Make sure the recommended coaches are for the user who is using this system
B06 | Workout assignments after class | As a user I want to be assigned workout assignments after class So that I can do exercise under trainer’s guidance not only during live class but also at any time I have spare time. | very low | 5 | ·Verify the assignments are updated after every workout.
B07d | Fast favorable review | As a user I want to give fast favorable reviews to trainers So that it does not cost much time to give favorable reviews and I can more directly see the users’ evaluation of the trainers. | very low | 5 | ·Verify a button of 'thumb up' is shown in each trainer page. ·Verify that the number of 'like' is near the button
|  | This is an example. This is a new line • Point 1 • Point 2 • Point 3 |  |  | This is an example. This is a new line 1. List 1 2. List 2 3. List 3