## Sheet1
Story ID | Story Name | Description | Priority | Iteration (Sprint) number | Acceptance Criteria | Notes | Date started (actual date) | Date finished (actual date)
|  | This is an example. This is a new line • Point 1 • Point 2 • Point 3 |  |  | This is an example. This is a new line 1. List 1 2. List 2 3. List 3
US01 | User sign up | As a user I want I can sign up the system with my telephone number/email together with some optional body characteristic. So that coach or the system can better custom some classes for me. |  |  | Make sure the telephone number/ email is not used by other people Receive the user’s phone/email, name,password, gender(o), weight(o), height(o), age(o) Generate user entity with above information, store in the memory.
US02 | User sign up legality | As a staff of the gym I want the user sign up procedure can make sure the phone/email is legal and password is encrypted So that the system can be more safe |  |  | Make sure the phone/email is legal Make sure the stored password is encrypted once stored in memory | implementation of US01
US01G | User sign up GUI | As a staff of gym I want the sign up surface is clean and easy to use, where have some notice to introduce user to sign up So that it will not let people who want to register to give up because of the complicated interface |  |  | Make sure there is sign up link in sign in interface Make sure there is only email/phone, password, name , weight height shown Make sure the sign up procedure is done with continuously interface for good design
UL01 | User log in | As a user I want I can sign in just with my phone/email and password So that i can save more time |  |  | Use email/phone as ID of the user Use password to make sure if the user have the authority to login If password wrong, show the message If user entity not exist, show the message.
UL01G | user login GUI | As a staff I want the GUI of login can be shown once user open the system and after the login procedure, it will jump to the home page So that i can have better user experiment |  |  | Once the system start, the login page will show out After the login procedure finish, it will change to the home page
MS01 | Set up different membership | As a user I want to get higher membership when I recharge more money and get So that I can enjoy some specific service |  |  | According to the money that they recharged, they can set to different membership Once a recharge procedure finish, check if the total recharged money is enough to upgrade membership For different membership, set up some rights for them to use
MS02 | Set up bargain for recharge money | As a staff I want the more money they recharge, the more bargain they can get So that user will be likely to deposit more money to the system |  |  | Set different bargain for different deposit level Receive the user id, return current money and update membership
MS03 | Set up 7 day free for video | As a staff I want the new user can try to use the system without limitation for 7 days So that they can adapt to the system and can increase user retention |  |  | Set create time for user entity to compute the day to decide whether he can user the privilege Check the authority when the user update
MS04 | Invitation code | As a user I want that new users can register with old user’s invitation code. So that both the new and old users are able to earn some discount. |  |  | Generate and store the user’s invitation code and compare them when needed. Design the discount strategy.
MS05 | Family membership | As a user I want that users can register and purchase membership card in family unit. So that the whole family can share the membership and get some discount |  |  | Set different membership type and design different membership discount strategy
MS06 | Family membership for kids | As a user I want that kids can have discount or be free of charge in family membership. So that it will be more attractive to the family with kids. |  |  | Set different membership type and design different membership discount strategy.
MS05 | Reliable data storage | As a staff I want a reliable data storage system during our developing process. So that it will be safer to store the user’s data. |  |  | Design and implement a well design data storage interface